## Sheet1
№ | Tasks | Members | Start Time | End time | S | M | A | R | Designations
1 | Problem Analysis and gathering information | Yeszhanov Madi Aripov Rasul | 2020-10-05 | 2020-10-31 | Find information about our problem and analyse it for finding solution | Count of found material = 3 | At least 5 science materials related to problem | Yes, because we need to know the problems of this topic | Achived | In Progress | Rejected | In the plan
2 | UML model of our project | Yeszhanov Madi Aripov Rasul | 2020-11-01 | 2020-11-30 | Create an model to understand how the system of our project works | Clarity = 0 Implementability = 0 Correctness = 0 | Clarity, Implementability and Correctness should be at least 75% | Yes, because it will help us implement our project and reduce some incorrectnes in system
3 | Database design | Aripov Rasul | 2020-12-01 | 2020-12-06 | Create a link model in the database | Normalization = N0 | At least N3 level of normalization for each table | Yes, because it help us create right database and eliminate some errors in it
4 | Database creation | Yeszahnov Madi | 2020-12-07 | 2020-12-18 | Create a database | Correctness with database model = 0 | Correctness of database with model should be 95% | Yes, we need database to store the information
5 | Database population | Yeszhanov Madi Aripov Rasul | 2020-12-19 | 2020-12-29 | Adding information to the database | Count of records = 0 | Count of records should be at least 500 rows | Yes, we need information to show it on system
6 | Back-end: Admin panel for database | Yeszahnov Madi | 2021-01-04 | 2021-01-18 | Create an admin panel for database manipulation | Page load time = 0 Error Rate= 0 | Page load time = nlog(n) Error Rate= less then 15% | Yes, we need to control database from site
7 | Back-end: Registration and login system | Aripov Rasul | 2021-01-04 | 2021-01-24 | Create a registration system for creating acounts | Page load time = 0 Error Rate= 0 | Page load time = nlog(n) Error Rate= less then 15% | Yes, we need it to provide more capabilities to people who logged in
8 | Back-end: User profile and User capabilities | Aripov Rasul | 2021-01-24 | 2021-02-07 | Create a user profile and add some features | Page load time = 0 Error Rate= 0 | Page load time = nlog(n) Error Rate= less then 15% | Yes, we need it to provide more capabilities to people who logged in
9 | Back-end: Search engine | Yeszahnov Madi | 2021-01-19 | 2021-02-07 | Create a search engine by name of drug or by alphabet order | Page load time = 0 Error Rate=0 | Page load time = nlog(n) Error Rate= less then 15% | Yes, users needs to find what they need
10 | Back-end: Pill identifier | Aripov Rasul | 2021-02-08 | 2021-02-21 | Create a search drug by pills properties | Page load time = 0 Error Rate= 0 | Page load time = nlog(n) Error Rate= less then 15% | Facilitate drug search if the name is not known but the characteristics of the pill are known
11 | Back-end: Side Effects | Yeszahnov Madi | 2021-02-08 | 2021-02-21 | Create a search drugs by side effects | Page load time = 0 Error Rate= 0 | Page load time = nlog(n) Error Rate= less then 15% | Facilitate drug search by knowing of side effects and select the needed drug by including or excluding this side effects
12 | Back-end: Mapping of local and international drug names | Yeszahnov Madi | 2021-02-21 | 2021-03-07 | Create mapping of local names to internation and vice versa | Page load time = 0 Error Rate= 0 | Page load time = nlog(n) Error Rate= less then 15% | Facilitate drug search by local and international names to increase the possible choices of needed drugs
13
14 | Front-end: UX analysis | Aripov Rasul | 2021-03-22 | 2021-03-28 | Conduct the analysis of target user | Number of people was involved to analysis = 0 | Number of people was involved to analysis = 5 | Yes, to improve expirience of using this site for target user
15 | Front-end: UI design | Yeszahnov Madi | 2021-03-29 | 2021-04-04 | Design site GUI model | Following the results we gained from analysis = 0% | Following the results we gained from analysis = 75% | Yes, to implement right makeup to site
16 | Front-end: GUI implementation | Yeszhanov Madi Aripov Rasul | 2021-05-04 | 2021-04-18 | Implement HTML and CSS markup of GUI model | Correctness with GUI model = 0% | Correctness with GUI model = 80% | Yes, to implement GUI for our site
17 | Testing and debugging | Yeszhanov Madi Aripov Rasul | 2021-04-19 | 2021-05-31 | Conduct testing in each page and fix the errors | Count of pages we conduct the tests = 0 | Count of pages we conduct the tests = 4 | Yes, to reduce count of errors in our site